## Sheet1
Task Name | Estimate | Start Date | Task Owner | Assumptions / Known Issues / Notes
Project Problem Statement | 1 days | 2020-03-29 | Mark Jones
Project Plan | 1 days | 2020-03-29 | Mark Jones
Get Project Approved | 3 days | 2020-04-01 | Jason Jenkins
Interview Potential Users | 2 days | 2020-04-03 | Adhoc Team
Document Requirements | 3 days | 2020-05-08 | Mark Jones
Finalize Requirements | 1 days | 2020-05-08 | Mark Jones
Design Classes | 5 days | 2020-05-08 | Mark Jones
Document Technical Design | 3 days | 2020-05-08 | Mark Jones | Include version control system, language, IDE, etc.
Design User Interface | 5 days | 2020-05-08 | Mark Jones
Create Code Classes | 5 days | 2020-05-08 | Mark Jones
Create User Interface | 5 days | 2020-05-08 | Mark Jones
Write code for features | 10 days | 2020-05-08 | Mark Jones
Connect Code Classes to UI | 3 days | 2020-05-08 | Mark Jones
Write Test Cases | 3 days | 2020-05-08 | Mark Jones
Finalize Code | 1 days | 2020-05-08 | Mark Jones
Code Review | 1 days | 2020-05-08 | Mark Jones
Test Code - Development | 1 days | 2020-05-08 | Mark Jones
Deploy Program | 1 days | 2020-05-08 | Mark Jones | Acquire Test Data
Test Deployment | 1 days | 2020-05-08 | Mark Jones
Fix Issues | 2 days | 2020-05-08 | Mark Jones
Submit Program | 0 days | 2020-05-08 | Mark Jones